## Sheet1
Task List and Assignment
Week 1 (6/09 - 6/15) | · Discuss with Prof. Yuting Zhang. (All) · Choose project topic (All) · Group meeting (All)
Week 2 (6/16 - 6/22) | · Write project proposal (All) · Read related papers (All) · Design simulator module (All) · Design user interface (All) · Group meeting (All)
Week 3 (6/23 - 6/29) | · Read G-EDF and PF algorighm research papers (Junjie Wang) · Read P-EDF algorithm research papers (Xin Shan) · Read LLF algorithm research papers (Yingyuan Zhang) · Read other related multiprocessors CPU scheduling paper (All) · Analyse and introduce algorithms (Junjie Wang) · Implement user interface (Xin Shan, Yingyuan Zhang) · Implement simulator module (Xin Shan, Yingyuan Zhang) · Group meeting (All)
Week 4 (6/30 - 7/06) | · Implement user interface (Xin Shan, Yingyuan Zhang) · Implement simulator module (All) · Testing (Junjie Wang) · Group meeting (All)
Week 5 (7/07 - 7/13) | . Implement user interface (Xin Shan, Yingyuan Zhang) . Implement simulator module (All) . Group meeting (All)
Week 6 (7/14 - 7/20) | · Implement simulator module (All) · Group meeting (All)
Week 7 (7/21 - 7/27) | · Integrate simulator module (All) · Testing (All) · Write final paper (All) · Prepare presentation (All) · Group meeting (All)
Week 8 (7/29) | · Presentation (All)